## Mason Training Task Logsheet
Mason Training Task Logsheet
2026-07-29 | today |  |  |  | days left until graduation:
2020-02-29 | graduation date |  |  |  | -1673
Step | Activity |  | Responsible | Due Date | days before deadline | Deadline | done
|  | make notes here | [Team/ Name] | [days before graduation]
1 | General Decisions for Mason Training (1 week)
1.1 | Process manager is selected |  |  | 70 | -1743 |  | x
1.3 | Woreda of practical training is selected |  |  | 70 | -1743 |  | x
1.4 | Agreement of Woreda is received |  |  | 67 | -1740
1.5 | Site(s) for practical training is/ are selected: |  |  | 65 | -1738 |  | x
2 | Technical Preparation for training site(s) (1 week)
2.1 | Profile(s) is/ are taken |  |  | 63 | -1736
2.2 | Site design(s) is/ are done and approved |  |  | 60 | -1733
2.3 | Bill(s) of Quantities is/ are calculated |  |  | 59 | -1732
2.4 | Assessment of required construction material is available |  |  | 58 | -1731
3 | Administration and Organization (1 week)
3.1 | Number of trainees is set |  |  | 57 | -1730
3.2 | Payment level of trainees is confirmed by MGMT |  |  | 55 | -1728
3.3 | Budget is calculated, including: |  |  | 52 | -1725
· theoretical training,
· trainees per diem and payment schedule.
Budget is approved
3.4 | ToRs for Adadale college and MoUs are prepared |  |  | 52 | -1725
3.5 | Contract with Adadale college is signed |  |  | 50 | -1723
3.6 | MoU(s) for PADO/ GIZ/ Adadale |  |  | 48 | -1721 |  |  | do we have two separate MoUs?
3.7 | Trainees are invited and MoUs with Trainees are signed |  |  | 48 | -1721
3.8 | Advance payment request for Adadale College for material purchase has been requested |  |  | 50 | -1723
3.9 | Advance payment is approved and paid
3.10 | Payment schedule for trainees is set |  |  | 50 | -1723
4 | Preparation on site
4.1 | Storage level of cement in close woreda storages is assessed |  |  | 53 | -1726 | 2020-01-07
4.2 | Amount of cement needed is assessed |  |  | 51 | -1724 | 2020-01-09
4.3 | Procurement of cement has started |  |  | 49 | -1722 | 2020-01-11
4.4 | Toolkits are procured |  |  | 42 | -1715 | 2020-01-18
5 | Transportation and other suport
5.1 | Transport requirements for material and trainees are calculated |  |  | 50 | -1723
5.2 | Contractors for transportation are contacted |  |  | 50 | 7
5.3 | Contracts for delivery of water are signed |  |  | 48 | -1721
5.4 | Contract for delivery of stones and sand are signed |  |  | 43 | -1716
6 | Start of theoretical training in Adadale (3 weeks)
6.1 | Trainees take passport sized pictures at college for certificates |  |  | 42 | -1715
6.2 | Pictures of trainees are sent to Addis |  |  | 36 | -1709
7 | Start of practical training in Selected Woreda (3 weeks)
7.1 | Site(s) is/ are set out |  |  | 31 | -1704
7.2 | Community Facilitator(s) is/ are in place |  |  | 31 | -1704
7.3 | 50 % of necessary stones are unloaded on site(s) |  |  | 22 | -1695
7.4 | Water is available at site |  |  | 22 | -1695
7.5 | Cement is available at site |  |  | 22 | -1695
7.6 | 75% of excavation is done |  |  | 22 | -1695
7.7 | Trainees have arrived at Woreda of practical training |  |  | 22 | -1695
8 | Preparation of Graduation Ceremony
8.1 | Graduation location is set |  |  | 21 | -1694
8.2 | Budget for graduation is calculated (incl. per diems for partners, refreshments, etc.) |  |  | 18 | -1691
8.3 | Invitation letters for graduation ceremony are sent |  |  | 14 | -1687
8.4 | Participants from GIZ are selected |  |  | 14 | -1687
8.5 | Participation list for graduation ceremony is finalised and communicated to F&A team |  |  | 10 | -1683
8.6 | Certificates are printed and laminated |  |  | 7 | -1680
8.7 | Mason Toolkits are delivered |  |  | 7 | -1680
8.8 | Sound system and generator available |  |  | 3 | -1676
9 | Responsibilities, if sites are not finished by end of practical training time, are set.
10 | Finish practical training.
11 | Graduation ceremony.
12 | MoU for WSW site handing over signed.
Formulas:
Deadline = +B5-[Due Date]